AI OPERATIONS SYSTEM Detailed Study & Development Plan

| Client CAR-AGENTS | Prepared by McKH Technologies |
| --- | --- |

| Timeline 4 Weeks | Document Version v2.0 — Detailed Plan |
| --- | --- |

# 1. Executive Summary

CAR-AGENTS is a founder-led automotive brokerage that depends on fast lead response, disciplined follow-up, organized document handling, and consistent customer communication. This document provides the detailed study and development plan for the AI Operations System — including task-level breakdowns showing exactly which n8n node, API, or service powers each piece of work, along with realistic time estimates.

## 1.1 Expected Business Impact

| Area | Current State | After System |
| --- | --- | --- |
| Lead Capture | Manual, often missed | Near 100% automated logging |
| First Response Time | Hours or next day | 30–60% faster turnaround |
| Follow-up Discipline | Relies on memory | 70–85% fewer missed follow-ups |
| Daily Admin | 1–2 hrs of manual effort | Automated digest saves 1–2 hrs/day |
| Communication History | Scattered across apps | One unified CRM timeline |
| Document Handling | Inconsistent folder naming | Structured Drive with CRM links |
| Meeting Actions | Notes lost or forgotten | Auto-extracted tasks via voice AI |

# 2. Recommended Tech Stack & Integration Method

Every tool below is connected to n8n through either a native node or a direct API call. This table shows exactly how each piece talks to the others.

| Tool | Connects via | Integration Detail |
| --- | --- | --- |
| HubSpot Free CRM | n8n HubSpot node (OAuth 2.0 / Private App) | Native n8n node — create/update contacts, deals, tasks, notes. Real-time webhook triggers are limited on Free tier, so changes are detected via scheduled polling (every 5 min) instead of instant push triggers. |
| Gmail | n8n Gmail node (OAuth 2.0) | Native n8n node — trigger on new email, send email, label/archive. Used for inbound lead capture and outbound logging. |
| Google Drive | n8n Google Drive node (OAuth 2.0) | Native n8n node — create folders, upload files, move/rename. Used to build and maintain the client/deal folder structure automatically. |
| WhatsApp Business | n8n WhatsApp Business Cloud API node / webhook | Official Meta Cloud API via n8n's WhatsApp node — inbound messages arrive via webhook, outbound replies sent via API call. Requires Meta Business verification before webhook goes live. |
| Claude API | n8n HTTP Request node (Anthropic API) | No native n8n node — calls Anthropic's /v1/messages endpoint directly via HTTP Request node. Used for summarization, classification, drafting, and the daily brief. |
| Whisper / Transcription | n8n HTTP Request node (OpenAI Whisper API) | Voice notes forwarded via webhook, sent to Whisper API for transcription, text returned to n8n for further processing by Claude. |
| Google Sheets (optional) | n8n Google Sheets node (OAuth 2.0) | Used only if lightweight reporting beyond HubSpot's dashboard is needed. |

## 2.1 Important Technical Notes

- HubSpot Free fully supports n8n's native HubSpot node for creating/updating contacts, deals, tasks, and notes — zero issues for this use case

- All standard read/write operations work on the Free tier with no restrictions

- Real-time webhook triggers (e.g. "the moment a deal moves to Won, do X") require HubSpot Professional/Enterprise

- Workaround: n8n Schedule Trigger polls HubSpot every 5 minutes instead of instant push — not a dealbreaker for a 1-person operation

- HubSpot requires OAuth 2.0 or Private App tokens for all API access as of 2026 — old-style API keys no longer work

- This is a one-time setup detail during Week 1, not an ongoing limitation

- WhatsApp connects via n8n's WhatsApp Business Cloud API node — inbound via webhook, outbound via API call

- Requires Meta Business verification to be completed before the webhook can go live

- Claude has no native n8n node — it is called directly via the HTTP Request node against the Anthropic API

# 3. Sprint Breakdown — Week by Week

WEEK 1 — Discovery, Process Mapping & CRM Setup

## 3.1 Goal

Understand exactly how CAR-AGENTS operates today. Define the lead lifecycle, deal pipeline stages, and data structure. Set up HubSpot as the central operating hub and Google Drive as the document backbone.

## 3.2 Task Breakdown

| Task | n8n / API / Service Used | Estimated Time |
| --- | --- | --- |
| Kickoff meeting — capture full current workflow | Manual / Zoom or in-person | 3–4 hours |
| Map current lead sources (WhatsApp, email, referral, walk-in) | Manual review of client data | 2–3 hours |
| Define lead qualification criteria and scoring logic | Manual — business logic definition | 2 hours |
| Define deal pipeline stages | HubSpot — Deal Pipeline settings | 2–3 hours |
| Start WhatsApp Business verification process | Meta Business Manager / Cloud API onboarding | 1–2 hours (review takes 1–2 weeks) |
| Set up HubSpot Private App / OAuth 2.0 credentials | HubSpot — Private App settings (required for n8n) | 1 hour |
| Configure HubSpot account — contacts, companies, deals, tasks | HubSpot Admin + n8n HubSpot node (test connection) | 4–6 hours |
| Create custom HubSpot properties (lead source, vehicle type) | HubSpot — Properties settings | 3–4 hours |
| Set up Google Drive folder structure | Google Drive + n8n Google Drive node | 2–3 hours |
| Define document naming conventions | Manual — documented standard | 1–2 hours |
| Provision n8n instance (VPS, domain, SSL) | n8n self-hosted — VPS (Hetzner/DigitalOcean) | 1–2 days |
| Draft implementation spec for Weeks 2–4 | Manual — Google Doc | 4–5 hours |
| Confirm automation approval rules | Manual — policy decision with owner | 1–2 hours |

## 3.3 Week 1 Deliverables

| Deliverable | Format | Notes |
| --- | --- | --- |
| CRM Architecture Document | PDF / Google Doc | Full field mapping, pipeline stages, property list |
| HubSpot Live Configuration | HubSpot + Private App | Working CRM with OAuth 2.0 credentials ready for n8n |
| Google Drive Folder Structure | Google Drive | Standardized folders with naming convention guide |
| n8n Instance | Self-hosted VPS | Live and ready for Week 2 workflow building |
| WhatsApp Verification | Meta Business Manager | Submitted and in review — required before Week 2 WhatsApp build |
| Implementation Specification | Google Doc | Blueprint for Weeks 2–4 development |

WEEK 2 — Communication Integration

## 3.4 Goal

Connect Gmail and WhatsApp to HubSpot via n8n so that every inbound and outbound message is automatically captured in the CRM timeline. Build the task-trigger logic so that conversations generate follow-up tasks without manual entry.

## 3.5 Task Breakdown

| Task | n8n / API / Service Used | Estimated Time |
| --- | --- | --- |
| Connect Gmail via OAuth 2.0 | n8n Gmail node | 3–4 hours |
| Build inbound email capture workflow | n8n Gmail Trigger node → HubSpot node | 4–6 hours |
| Build outbound email logging workflow | n8n Gmail node → HubSpot Engagements API | 3–4 hours |
| Confirm WhatsApp webhook is live (post-verification) | Meta Cloud API + n8n Webhook node | 1–2 hours |
| Build WhatsApp inbound message capture | n8n WhatsApp node (webhook) → HubSpot node | 4–6 hours |
| Map messages to correct HubSpot contact/deal | n8n Function node + HubSpot Search API | 4–5 hours |
| Build activity logging rules (calls, notes, emails) | n8n HubSpot node — Engagements API | 3–4 hours |
| Build task-trigger rules from inbound messages | n8n IF/Switch node → HubSpot Tasks API | 4–5 hours |
| Build HubSpot change-detection (polling, since no live webhook) | n8n Schedule Trigger (every 5 min) → HubSpot node | 2–3 hours |
| Build draft reply generation flow | n8n HTTP Request node → Claude API | 3–5 hours |
| Test end-to-end email and WhatsApp flow with dummy data | n8n manual execution + HubSpot sandbox records | 3–4 hours |

## 3.6 Week 2 Deliverables

| Deliverable | Format | Notes |
| --- | --- | --- |
| Email Capture Workflow | n8n workflow | Inbound lead emails logged to HubSpot automatically |
| WhatsApp Capture Workflow | n8n workflow | Inbound WhatsApp messages logged via Meta Cloud API |
| HubSpot Polling Workflow | n8n Schedule Trigger | 5-minute polling replaces unavailable real-time webhooks |
| Task Trigger Logic | n8n workflow | New message → task created in HubSpot |
| Draft Reply Generator | n8n + Claude API | AI drafts reply for owner review and approval |
| Unified Activity Timeline | HubSpot CRM | All communications visible in one place per contact |

WEEK 3 — AI Intelligence Layer

## 3.7 Goal

Add the Claude-powered intelligence layer that transforms raw data into structured, useful outputs — lead summaries, conversation summaries, reply drafts, voice transcription, action-item extraction, and the daily executive brief.

## 3.8 Task Breakdown

| Task | n8n / API / Service Used | Estimated Time |
| --- | --- | --- |
| Build AI lead summarization workflow | n8n HTTP Request → Claude API → HubSpot Notes API | 4–6 hours |
| Build conversation summarization workflow | n8n HTTP Request → Claude API | 4–5 hours |
| Build reply draft generation with tone matching | n8n HTTP Request → Claude API (custom prompt) | 3–5 hours |
| Set up Whisper transcription service | n8n HTTP Request → OpenAI Whisper API | 3–4 hours |
| Build voice-to-action workflow | n8n: Webhook → Whisper API → Claude API → HubSpot Tasks API | 5–7 hours |
| Build action-item extraction from transcripts | n8n HTTP Request → Claude API (structured JSON output) | 3–5 hours |
| Build stale deal detection | n8n Schedule Trigger → HubSpot Deals API (filter by last activity) | 3–4 hours |
| Build overdue task detection and escalation | n8n Schedule Trigger → HubSpot Tasks API | 2–3 hours |
| Build daily executive brief automation | n8n Schedule Trigger → HubSpot API + Claude API → Gmail/WhatsApp send | 5–7 hours |
| Test all AI workflows with real sample data | n8n manual execution with client-provided samples | 4–6 hours |
| Tune Claude prompts based on output quality | Claude API — prompt iteration | 3–4 hours |

## 3.9 Week 3 Deliverables

| Deliverable | Format | Notes |
| --- | --- | --- |
| AI Lead Summary | n8n + Claude + HubSpot | Auto-summary on every new inbound lead |
| AI Conversation Summary | n8n + Claude | Thread summarized and logged as HubSpot note |
| Reply Draft Output | Claude API → owner inbox | Draft reply for approval before sending |
| Voice-to-Task Workflow | n8n + Whisper + Claude | Voice note → transcript → summary → tasks |
| Daily Executive Brief | n8n + Claude → Gmail/WhatsApp | Morning digest of leads, tasks, risks, priorities |
| Silent Deal Alerts | n8n + HubSpot Deals API | Flags deals with no activity beyond threshold |

WEEK 4 — Testing, Hardening, UAT & Handover

## 3.10 Goal

Stabilize all workflows, run full functional and user acceptance testing with real business scenarios, harden error handling and retries, document the operating SOPs, train the owner, and deliver a production-ready system.

## 3.11 Task Breakdown

| Task | n8n / API / Service Used | Estimated Time |
| --- | --- | --- |
| Smoke testing — all workflows run without crash | n8n — manual execution of every workflow | 1 day |
| API integration testing | HubSpot, Claude, Gmail, WhatsApp, Drive, Whisper APIs | 1–2 days |
| Functional testing — end-to-end per workflow | n8n test executions against test matrix | 2 days |
| UAT Session 1 — owner tests with live data | Live walkthrough in HubSpot + WhatsApp | Half day |
| Bug fixing and iteration from UAT Session 1 | n8n workflow edits | 1–2 days |
| UAT Session 2 — validate fixes and edge cases | Live walkthrough | Half day |
| Error handling — retries, fallback logic, failure alerts | n8n Error Trigger node + retry settings | 1–2 days |
| Webhook monitoring — confirm reliable triggers | n8n execution logs (Gmail, WhatsApp webhooks) | Half day |
| Write operating SOPs | Manual — Google Doc | 1 day |
| Owner training session | Live walkthrough (recorded) | 2–3 hours |
| Final handover — credentials, workflow map | Manual — secure document handoff | Half day |
| 1-week post-launch monitoring | n8n execution logs + manual check-ins | Ongoing |

## 3.12 Week 4 Deliverables

| Deliverable | Format | Notes |
| --- | --- | --- |
| Tested Production Workflows | n8n + HubSpot + all tools | All workflows live, tested, and stable |
| UAT Report | Document | Pass/fail for each test scenario |
| Operating SOPs | PDF / Google Doc | Step-by-step guides for owner |
| Owner Training Recording | Video | Walkthrough session recorded for reference |
| Handover Documentation | Document | All credentials, workflow map, API details |
| Post-Launch Support Period | 1 week | Bug fixes only; monitored by McKH Tech |

# 4. Time Risk Register

This section identifies every component known to take meaningful time, with a single realistic estimate for planning purposes.

| Item | Estimated Time | Why It Can Take This Long |
| --- | --- | --- |
| WhatsApp Business verification | 1–2 weeks | Meta manually reviews business documents via the Cloud API onboarding flow; can require resubmission if details don't match exactly |
| HubSpot OAuth / Private App setup | 1 day | By 2026, HubSpot requires OAuth 2.0 or Private App tokens — old API keys no longer work. One-time setup, not a recurring blocker |
| HubSpot real-time triggers | N/A — workaround used | Instant webhook triggers need HubSpot Professional/Enterprise. Free tier uses 5-minute polling via n8n Schedule Trigger instead — fully workable for a 1-person operation |
| n8n VPS setup & SSL/domain | 2 days | Server provisioning, DNS propagation, and SSL certificate issuance |
| Claude API key & rate limits | Half day | Account setup and initial usage tier confirmation |
| Gmail OAuth / Drive auth | Half day | Workspace admin approval and consent screen setup |
| Whisper/transcription integration | 1 day | Audio format standardization and webhook wiring |
| n8n workflow debugging (all flows) | 3 days | Edge cases in message parsing, contact matching, and webhook reliability across all integrations |
| Claude prompt tuning (summaries, brief) | 2 days | Iterative — quality improves over 2–3 rounds with real sample data |
| UAT and feedback rounds | 2 days | Owner testing and fix cycles before launch |

## 4.1 Action Items to Protect the Timeline

- Start WhatsApp Business verification on Day 1 of Week 1 — it has the longest lead time and blocks Week 2 WhatsApp work

- Set up HubSpot Private App / OAuth 2.0 credentials early — old API keys will not work

- Use n8n Schedule Trigger polling (every 5 min) instead of real-time HubSpot webhooks — fully sufficient for this volume

- Provision the n8n VPS during Week 1 so DNS/SSL is ready before Week 2 development begins

# 5. Ongoing Operating Costs

The system is designed to run at low monthly cost. The following estimates are based on a small-volume founder-led business.

| Item | Est. Monthly Cost | Notes |
| --- | --- | --- |
| HubSpot Free CRM | $0 | Free tier; covers all needed read/write operations via n8n |
| n8n (self-hosted VPS) | $5–$20/mo | Hetzner/DigitalOcean; adequate for this volume |
| Claude API | $5–$30/mo | Depends on message volume and brief frequency |
| Google Workspace | $6–$12/mo | Per user; may already be in use |
| WhatsApp Business API | $0–$15/mo | Free tier for low volume; per-message cost above threshold |
| Whisper / Transcription | $2–$10/mo | OpenAI Whisper API; scales with recording volume |
| Domain / Hosting (n8n VPS) | $5–$20/mo | One-time setup; ongoing server cost |
| TOTAL ESTIMATE | ~$23–$107/mo | Depends on usage volume and upgrade decisions |

## 5.1 Cost Notes

- HubSpot Free is sufficient — n8n's native HubSpot node handles all needed contact/deal/task/note operations

- Claude API cost depends almost entirely on how frequently the daily brief, summaries, and draft replies are generated

- WhatsApp Business API is free under ~1,000 conversations/month; cost starts above that threshold

- If a VPS is already available from another service, hosting cost may be zero

McKH Technologies  |  Confidential  |  Prepared for CAR-AGENTS